Full Task & Work-Track Plan

AI-Based Pothole Severity Detection & Road Damage Prioritization

Every task, broken into sub-steps, deliverables, and time estimates — organized across 8 phases and 15 weeks

Academic Year Capstone Project — NMIMS Hyderabad

# How to Use This Plan

- Each phase below has a table of tasks. Every task is broken into concrete sub-steps so you always know the next action, not just the goal.

- Estimated effort (Est.) is in working days, assuming solo, part-time work (roughly 12-15 hrs/week) — adjust to your own pace.

- Phases 4 and 5, and Phases 6 and 7, run in parallel — don't treat this as a strict waterfall.

- Tasks marked (Stretch) in Phase 6 are optional — skip them without weakening the paper if time runs short.

| Phase 1 — Literature Review & Planning | Weeks 1-2 |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Survey existing literature | Read 10-15 papers on pothole detection (YOLO/Mask R-CNN based), road-damage datasets (RDD2022 papers), and pavement condition index (PCI) literature. Keep a running spreadsheet of paper, method, dataset, and reported metrics. | Annotated bibliography / related-work notes | 3d |
| 2 | Identify the research gap explicitly | Write a one-paragraph statement of what's missing in prior work (severity quantification, multi-criteria prioritization) — this becomes your Introduction's core claim. | Research-gap statement | 1d |
| 3 | Draft Related Work section (rough) | Turn the annotated bibliography into a structured draft — group by detection-only papers, dataset papers, PCI/civil-engineering severity literature. | Related Work draft v0 | 2d |
| 4 | Shortlist candidate datasets | List RDD2022, Kaggle pothole sets, Roboflow Universe sets, Pothole-600/CNRDD, Indian Roads segmentation set with size/format/license for each. | Dataset shortlist table | 1d |
| 5 | Verify dataset access and licensing | Actually visit each link, confirm the dataset downloads, check license terms permit academic use and redistribution of a merged/derived set. | Confirmed dataset list (3-4 sources) | 1d |
| 6 | Finalize project scope decisions | Lock in: primary detector (YOLOv8-seg), stretch goal (open-vocab), and what gets cut if time runs short (from the Feasibility section). | Signed-off scope document | 0.5d |

| Phase 2 — Dataset Preparation | Weeks 2-4 |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Download all shortlisted datasets | Pull RDD2022, Kaggle/Roboflow pothole sets, Indian Roads segmentation, and Pothole-600 into data/raw/, keeping each source in its own subfolder. | Populated data/raw/ | 1d |
| 2 | Standardize annotation format | Convert every dataset's annotations (VOC XML, COCO JSON, YOLO txt) into one common YOLO-seg format using conversion scripts. | Unified annotation schema | 2d |
| 3 | Convert boxes to masks where needed | For bounding-box-only datasets, run SAM (Segment Anything) prompted with each box to auto-generate a mask; manually spot-check and correct ~10-15%. | Segmentation masks for all sources | 3d |
| 4 | Deduplicate across datasets | Run perceptual hashing (imagehash library) across the merged pool to catch near-duplicate images pulled from overlapping sources. | Deduplicated data/merged/ | 1d |
| 5 | Clean noisy annotations | Manually review a random 10-15% sample per source; fix or discard clearly wrong boxes/masks. | Cleaned annotation set | 2d |
| 6 | Design the severity rating rubric | Write a explicit 1-5 rubric (1 = surface scuff ... 5 = deep pothole, exposed base/likely vehicle damage) with example images for each level. | Written rubric + example sheet | 1d |
| 7 | Select the severity validation subset | Pick 150-250 images spanning small/medium/large/deep potholes, covering multiple source datasets. | severity_val_subset/ folder | 1d |
| 8 | Recruit 2-3 independent raters | Line up teammates, classmates, or mentors willing to rate the subset independently using the rubric. | Confirmed rater list | 0.5d |
| 9 | Collect independent severity ratings | Each rater scores all images 1-5 independently, blind to each other's scores. | Raw rating spreadsheet | 2d |
| 10 | Compute inter-rater agreement | Calculate Cohen's kappa (2 raters) or Fleiss' kappa (3+) on the collected ratings; document the result. | Inter-rater agreement score + writeup | 0.5d |

| Phase 3 — Detection Model Development | Weeks 4-6 |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Set up training environment | Install Ultralytics YOLOv8, PyTorch with GPU support (Colab/Kaggle/local), verify CUDA availability. | Working training environment | 0.5d |
| 2 | Prepare data splits | Split merged dataset 70/15/15 (train/val/test), stratified by source dataset to avoid domain leakage. | train/val/test manifest files | 0.5d |
| 3 | Build augmentation pipeline | Add rain/glare simulation, motion blur, and brightness/contrast jitter to the training pipeline (Albumentations or YOLO's built-in augment config). | Augmentation config | 1d |
| 4 | Fine-tune YOLOv8-seg (baseline run) | Start from COCO-pretrained weights, fine-tune on the merged training set; log training curves. | First trained checkpoint | 2d |
| 5 | Tune hyperparameters | Iterate on learning rate, epochs, image size, and augmentation strength based on validation performance. | Tuned checkpoint | 2d |
| 6 | Evaluate detection metrics | Compute mAP@0.5, mAP@0.5:0.95, precision/recall per class, and mask IoU on the held-out test set. | Detection metrics report | 1d |
| 7 | Train Mask R-CNN baseline (Detectron2) | Fine-tune Mask R-CNN on the same data split for a fair accuracy/speed comparison table. | Baseline checkpoint + metrics | 2d |
| 8 | Document detection results | Write up the comparison table (YOLOv8-seg vs Mask R-CNN) with metrics, inference speed, and qualitative examples. | Detection results section draft | 1d |

| Phase 4 — Severity & Prioritization Modules | Weeks 6-9 |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Build geometric severity module | From each predicted mask, compute area ratio a = mask pixel area / estimated road-surface area in frame. | Area-ratio module (src/severity/geometric.py) | 1.5d |
| 2 | Build depth-proxy module | Run MiDaS/DPT on each image; compute relative depth differential between the pothole region and surrounding road as proxy d. | Depth-proxy module | 2d |
| 3 | Build fallback depth heuristic | Implement the shadow-darkness ratio heuristic as a lightweight fallback/validation check against the MiDaS-based proxy. | Shadow-heuristic module | 1d |
| 4 | Build structural irregularity module | Compute contour roughness i = perimeter^2 / (4*pi*area) from each mask's contour. | Irregularity module | 1d |
| 5 | Normalize and fuse the three cues | Implement S = 100*(w1*norm(a) + w2*norm(d) + w3*norm(i)); write normalization functions for each raw cue. | Fusion function (src/severity/fusion.py) | 1.5d |
| 6 | Calibrate fusion weights | Grid-search or manually tune w1/w2/w3 against the severity validation subset; optimize for Spearman's rho with human ratings. | Calibrated weights + rho score (target >= 0.7) | 2d |
| 7 | Build the prioritization formula | Implement P = alpha*S + beta*RoadTypeWeight + gamma*TrafficProxy + delta*RecurrenceFactor. | Prioritization function (src/prioritization/) | 1.5d |
| 8 | Source road-type weights from OSM | Query OpenStreetMap tags (highway=primary/secondary/residential) for each GPS location and map to weight 1.0/0.7/0.4. | Road-type weight lookup | 1d |
| 9 | Build traffic and recurrence proxies | Implement time-of-day/road-type traffic heuristic; implement GPS-cluster-based recurrence counting. | Traffic + recurrence modules | 1.5d |
| 10 | Run weight-sensitivity ablation | Test default vs traffic-heavy vs severity-only weighting; document how the ranking changes. | Ablation results table | 1d |

| Phase 5 — Application Integration | Weeks 7-11 (overlapping) |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Design database schema | Model tables for reports, detections, severity scores, priority scores, and status (in-progress/repaired) in PostgreSQL. | Schema + ER diagram | 1d |
| 2 | Set up PostgreSQL + PostGIS | Stand up the database (Docker container), enable PostGIS extension for geospatial queries. | Running database instance | 0.5d |
| 3 | Build FastAPI backend skeleton | Scaffold routes, schemas (Pydantic), and DB models; set up Alembic migrations. | Backend skeleton | 1d |
| 4 | Implement POST /api/report | Accept image + GPS upload, run inference pipeline (detect -> severity -> priority), store and return results. | Working upload+inference endpoint | 2d |
| 5 | Implement GET /api/potholes and /api/priority-list | List/filter potholes by severity, status, region; return ranked worklist. | Query endpoints | 1d |
| 6 | Implement PATCH /api/potholes/{id}/status | Allow admins to mark a pothole in-progress/repaired. | Status-update endpoint | 0.5d |
| 7 | Implement PDF report endpoint | Auto-generate a per-region summary PDF (ReportLab/WeasyPrint) from current data. | PDF report generator | 1.5d |
| 8 | Build citizen upload portal (React) | Mobile-friendly page: photo/video upload, auto-capture GPS+timestamp, submission status view. | Citizen-facing web app | 2.5d |
| 9 | Build admin map dashboard | Leaflet map with potholes color-coded by severity/priority; sortable/filterable worklist table. | Admin dashboard (map + table) | 2.5d |
| 10 | Add live weight sliders to admin dashboard | Expose alpha/beta/gamma/delta as sliders that re-rank the worklist in real time. | Interactive weight-slider UI | 1.5d |
| 11 | Connect pipeline end-to-end | Wire frontend -> backend -> inference pipeline -> database -> dashboard into one working flow. | Working end-to-end demo | 2d |
| 12 | Test on real captured images/video | Walk around campus/nearby roads, capture real photos/video, run them through the full system to catch integration bugs. | Real-world test log + bug list | 1d |

| Phase 6 — Evaluation & Experiments | Weeks 11-13 |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Run full detection metric suite | Recompute mAP@0.5, mAP@0.5:0.95, precision/recall, mask IoU on the final model for reporting. | Final detection metrics table | 0.5d |
| 2 | Run severity correlation evaluation | Compute Spearman's rho and MAE between predicted S and human ratings on the validation subset. | Severity evaluation table | 1d |
| 3 | Run prioritization ranking evaluation | Compute Kendall's tau vs an expert/simulated ideal repair order; compute Top-K precision for 'Critical' flags. | Prioritization evaluation table | 1d |
| 4 | Run severity fusion ablation | Compare full model vs area-only vs area+depth vs area+irregularity — this is the most important ablation. | Fusion ablation table | 1d |
| 5 | Run augmentation ablation | Compare detector trained with vs without rain/blur augmentation. | Augmentation ablation table | 1d |
| 6 | Run model-choice ablation | Finalize the YOLOv8-seg vs Mask R-CNN accuracy/speed trade-off table. | Model ablation table | 0.5d |
| 7 | Measure latency and throughput | Benchmark end-to-end inference latency (mean/95th percentile) and images/sec on available hardware (CPU vs GPU). | Performance benchmark table | 1d |
| 8 | (Stretch) Build open-vocabulary comparison | Run Grounding DINO/OWL-ViT with text prompts on the same test images; compare zero-shot vs fine-tuned performance. | Open-vocab comparison results | 2d (optional) |
| 9 | Collect and curate failure cases | Gather examples where the system fails (night images, occlusion, waterlogged potholes) for the Discussion section. | Failure-case gallery + notes | 1d |

| Phase 7 — Research Paper Writing | Weeks 10-14 (overlapping) |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Draft Introduction | Problem statement, research gap, and the three contributions (severity scoring, prioritization, optional open-vocab). | Introduction draft | 1d |
| 2 | Draft Related Work | Expand the annotated bibliography into a structured section covering detection papers, dataset papers, PCI literature. | Related Work draft | 1.5d |
| 3 | Draft Dataset section | Describe the merged dataset, severity validation subset, annotation process, and inter-rater agreement. | Dataset section draft | 1d |
| 4 | Draft Methodology section | Write up the detection model, severity fusion formula, and prioritization formula with full equations. | Methodology section draft | 1.5d |
| 5 | Draft Experiments section | Describe evaluation protocol: detection metrics, severity correlation, prioritization ranking, ablations, latency. | Experiments section draft | 1d |
| 6 | Draft Results & Discussion | Present tables/figures, compare to baselines, do error analysis with failure-case examples. | Results & Discussion draft | 2d |
| 7 | Draft Limitations and Conclusion | State the monocular-depth-proxy limitation, heuristic traffic proxy, subjective severity ground truth; outline future work. | Limitations + Conclusion draft | 1d |
| 8 | Get mentor/faculty review | Send the full draft for review; collect feedback. | Reviewed draft with comments | 0.5d (+ wait time) |
| 9 | Revise based on feedback | Incorporate review comments across all sections. | Revised draft | 1.5d |
| 10 | Final formatting and proofread | Format to target venue's template, proofread, check all citations and figure references. | Submission-ready paper | 1d |

| Phase 8 — Final Demo & Presentation Prep | Weeks 14-15 |
| --- | --- |

| # | Task | Sub-steps / How to do it | Deliverable | Est. |
| --- | --- | --- | --- | --- |
| 1 | Polish dashboard UI | Fix visual rough edges, add loading states, make sure the map and worklist look presentation-ready. | Demo-ready UI | 1d |
| 2 | Prepare live demo script | Script the exact flow: upload -> detection overlay -> severity card -> map -> live weight-slider re-ranking. | Written demo script | 0.5d |
| 3 | Prepare novelty-demonstration moments | Pre-select two similar-size/different-severity potholes to show side by side; prep the weight-slider toggle moment. | Demo asset list (images/examples) | 0.5d |
| 4 | Rehearse the demo end-to-end | Do at least 2-3 full run-throughs, timing each section, ironing out live-demo failure points. | Rehearsed, timed demo | 1d |
| 5 | Finalize presentation slides | Build slides covering problem, contribution, architecture, results, and live demo transition. | Final slide deck | 1.5d |
| 6 | Final paper and code submission | Submit the finalized paper, push final code to the repository, confirm all deliverables are in place. | Submitted paper + repo | 0.5d |

Total tasks: 61 across 8 phases. Treat the Est. column as rough planning input, not a hard commitment — recalibrate week to week against actual progress.